## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
| System Login | As a user, I want to choose my role (Student, MO, Admin), So that I can access my specific dashboard. | High | 1 | 1. Dropdown for roles matches UI.<br>2. Error message for wrong credentials.<br>3. Redirects to correct dashboard based on role. | 3 | UI shows BUPT brand. No DB used. | 2026-03-06 | 2026-03-12
| Data Persistence (File) | As a developer, I want to use text/JSON files for storage, So that data is saved without a database. | High | 1 | 1. System reads/writes to .txt or .json files.<br>2. Data integrity is maintained after app restart.<br>3. Supports CSV/JSON formats as per PDF. | 8 | MANDATORY: Do not use SQL/Spring Boot. | 2026-03-06 | 2026-03-15
| Profile & CV Management | As a Student, I want to edit my skills and upload a CV, So that I can be eligible for TA jobs. | High | 1 | 1. Fields: Name, Email, Skills (tags), Max Hours.<br>2. CV Upload button triggers file picker.<br>3. Successful "Save" feedback. | 5 | UI matches the "Profile & CV" mockup. | 2026-03-13 | 2026-03-22
| Post Job Opening | As a Module Organiser (MO), I want to create new job listings, So that students can apply. | High | 2 | 1. Inputs: Module Name/Code, Hours/Week, Duration.<br>2. Job status is set to "OPEN" by default.<br>3. New job updates the global job list file. | 5 | Required Core Function for MO. | 2026-03-23 | 2026-04-01
| Job Search & Browsing | As a Student, I want to search and filter available jobs, So that I find suitable positions quickly. | High | 2 | 1. Search bar filters by title/module code.<br>2. Job cards show Professor name, match %, and hours.<br>3. Pagination/Scrolling for long lists. | 5 | UI follows "Browse Jobs" tab design. | 2026-03-23 | 2026-04-05
| Application Submission | As a Student, I want to apply for a job with a cover letter, So that I can showcase my fit. | High | 2 | 1. "Apply Now" opens a modal (as per UI).<br>2. User can enter Cover Letter text.<br>3. Modal shows AI Match Analysis bar. | 3 | Links Student ID to Job ID in storage. | 2026-04-02 | 2026-04-12
| Application Review | As a MO, I want to Accept or Reject applicants, So that the TA recruitment is completed. | High | 3 | 1. List of applicants per job is visible to MO.<br>2. "Accept" and "Reject" buttons function correctly.<br>3. Status updates the student's dashboard. | 8 | Core hiring loop completion. | 2026-04-13 | 2026-04-25
| Application Tracking | As a Student, I want to see the status of my applications, So that I know if I was selected. | Medium | 3 | 1. Dashboard shows "PENDING", "ACCEPTED", "REJECTED" badges.<br>2. Badges are color-coded (Yellow/Green/Red).<br>3. Displays application date. | 3 | Improves user experience. | 2026-04-20 | 2026-05-03
| Admin Workload Chart | As an Admin, I want to see a visual chart of TA workloads, So that I can prevent overallocation. | Medium | 4 | 1. Bar chart displays Hours/Week for each TA.<br>2. Chart updates dynamically based on accepted jobs.<br>3. Clear X and Y axis labels. | 8 | UI matches "Admin Dashboard" mockup. | 2026-05-04 | 2026-05-15
| Capacity Alerts | As an Admin, I want to receive alerts when a TA is at max capacity, So that I can intervene. | Medium | 4 | 1. Alert box shows "WARNING" for 15h+.<br>2. "CRITICAL" alert for 18h-20h+.<br>3. Red/Yellow badges for easy visibility. | 5 | Requirement: Workload balancing. | 2026-05-04 | 2026-05-18
| AI Skill Match Logic | As a system, I want to calculate a match score based on skills, So that MOs find the best fit. | Low | 4 | 1. Compare Student skills vs Job required skills.<br>2. Display match % (e.g., 2/4 match = 50%).<br>3. Results must be explainable in Viva. | 8 | AI generated initial keyword matching; team modified to weighted skill matching for better explainability. | 2026-05-10 | 2026-05-24