## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned) | Feedback/Actions
1 | System Login | As a user, I want to choose my role (Student, MO, Admin), So that I can access my specific dashboard. | High | 1 | 1. Dropdown for roles matches UI. | 3 | UI shows BUPT brand. No DB used. | 2026-03-06 | 2026-03-12 | Feedback: Login/Register buttons too close → increased spacing (feedback.md)
2. Error message for wrong credentials.
3. Redirects to correct dashboard based on role.
2 | Data Persistence (File) | As a developer, I want to use text/JSON files for storage, So that data is saved without a database. | High | 1 | 1. System reads/writes to .txt or .json files. | 8 | MANDATORY: Do not use SQL/Spring Boot. | 2026-03-06 | 2026-03-15
2. Data integrity is maintained after app restart.
3. Supports CSV/JSON formats as per PDF.
3 | Profile & CV Management | As a Student, I want to edit my skills and upload a CV, So that I can be eligible for TA jobs. | High | 1 | 1. Fields: Name, Email, Skills (tags), Max Hours. | 5 | UI matches the "Profile & CV" mockup. | 2026-03-13 | 2026-03-22 | Feedback: No confirmation after CV upload → added "file attached" text (feedback.md)
2. CV Upload button triggers file picker.
3. Successful "Save" feedback.
4 | Post Job Opening | As a Module Organiser (MO), I want to create new job listings, So that students can apply. | High | 2 | 1. Inputs: Module Name/Code, Hours/Week, Duration. | 5 | Required Core Function for MO. | 2026-03-23 | 2026-04-01
2. Job status is set to "OPEN" by default.
3. New job updates the global job list file.
5 | Job Search & Browsing | As a Student, I want to search and filter available jobs, So that I find suitable positions quickly. | High | 2 | 1. Search bar filters by title/module code. | 5 | UI follows "Browse Jobs" tab design. | 2026-03-23 | 2026-04-05 | Feedback: Module name text too small → increased font size (feedback.md)
2. Job cards show Professor name, match %, and hours.
3. Pagination/Scrolling for long lists.
6 | Application Submission | As a Student, I want to apply for a job with a cover letter, So that I can showcase my fit. | High | 2 | 1. "Apply Now" opens a modal (as per UI). | 3 | Links Student ID to Job ID in storage. | 2026-04-02 | 2026-04-12 | Feedback: No back button on job detail → added "Back to List" link (feedback.md)
2. User can enter Cover Letter text.
3. Modal shows AI Match Analysis bar.
7 | Application Review | As a MO, I want to Accept or Reject applicants, So that the TA recruitment is completed. | High | 3 | 1. List of applicants per job is visible to MO. | 8 | Core hiring loop completion. | 2026-04-13 | 2026-04-25
2. "Accept" and "Reject" buttons function correctly.
3. Status updates the student's dashboard.
8 | Application Tracking | As a Student, I want to see the status of my applications, So that I know if I was selected. | Medium | 3 | 1. Dashboard shows "PENDING", "ACCEPTED", "REJECTED" badges. | 3 | Improves user experience. | 2026-04-20 | 2026-05-03
2. Badges are color-coded (Yellow/Green/Red).
3. Displays application date.
9 | Admin Workload Chart | As an Admin, I want to see a visual chart of TA workloads, So that I can prevent overallocation. | Medium | 4 | 1. Bar chart displays Hours/Week for each TA. | 8 | UI matches "Admin Dashboard" mockup. | 2026-05-04 | 2026-05-15
2. Chart updates dynamically based on accepted jobs.
3. Clear X and Y axis labels.
10 | Capacity Alerts | As an Admin, I want to receive alerts when a TA is at max capacity, So that I can intervene. | Medium | 4 | 1. Alert box shows "WARNING" for 15h+. | 5 | Requirement: Workload balancing. | 2026-05-04 | 2026-05-18
2. "CRITICAL" alert for 18h-20h+.
3. Red/Yellow badges for easy visibility.
11 | AI Skill Match Logic | As a system, I want to calculate a match score based on skills, So that MOs find the best fit. | Low | 4 | 1. Compare Student skills vs Job required skills. | 8 | AI generated initial keyword matching; team modified to weighted skill matching for better explainability. | 2026-05-10 | 2026-05-24 | TA suggestion: show top 3 missing skills → added to AC
2. Display match % (e.g., 2/4 match = 50%).
3. Results must be explainable in Viva.